## Schedule Analysis
Project Name | Project Duration | Start Date | End Date | Expected Completion Date | Current Project % Completion | % Schedule Slip | Probability of Project Completing on the expected Time
A | 10 | 2022-10-15 | 2023-07-31 | 2023-08-31 | 60% | 2.74% | 97.26% | Project Duration: 10 weeks
B | 6 | 2023-02-01 | 2023-07-31 | 2023-08-31 | 50% | 5.48% | 94.52% | Planned Start Date: 1st January 2023
C | 6 | 2023-02-20 | 2023-08-31 | 2023-09-30 | 25% | 19.18% | 80.82% | Planned Completion Date: 11th March 2023
D | 7 | 2023-02-01 | 2023-08-31 | 2023-09-30 | 60% | 8.22% | 91.78% | Actual Completion Date: 25th March 2023
E | 8 | 2023-12-16 | 2023-07-31 | 2023-08-31 | 60% | 2.74% | 97.26%
F | 6 | 2023-02-20 | 2023-08-31 | 2023-09-30 | 66% | 2.74% | 100% | Actual Progress = (Actual Completion Date - Planned Start Date) = 25th March 2023 - 1st January 2023 = 12 weeks
G | 7 | 2023-04-17 | 2023-10-17 | 2023-10-01 | 60% | 0% | 100%
H | 3 | 2023-04-10 | 2023-06-30 |  | 50% |  | 50% | Next, calculate the % Schedule Slip:
I | 6 | 2023-02-01 | 2023-07-31 | 2023-08-31 | 50% | 5..48% | 94.52%
% Schedule Slip = ((Actual Completion Date - Planned Completion Date) / Project Duration) * 100 % Schedule Slip = ((25th March 2023 - 11th March 2023) / 10 weeks) * 100 % Schedule Slip = (14 weeks / 10 weeks) * 100 % Schedule Slip = 140%
31st July 2023-15th oct 2023
% Schedule Slip = ((3rd August 2023 - 31st August 2023) / (10 months)) * 100 = (-28 days / 10 months) * 100 = -2.74% (rounded to 2 decimal places)
Probability of Project Completing on Expected Time = 100% - 2.74% = 97.26%
%

## Cost Analysis
Project Name | Total Milestones | Milestones Completed | % Milestone | Next Milestone Details
A | 5 | 3 | 60% | Phase 3 30%
Phase 4 10%
B | 4 | 2 | 50% | Training and UAT-25%
Go Live-25%
C | 8 | 2 | 25% | Configuration-10%
CRP- 10%
Training- 10%
UAT
Go-Live- 20%
Hyper-Care Support- 20%
D | 5 | 3 | 60% | Prod Upgrade- 20%
Go Live- 20%
E | 5 | 3 | 60% | Completion of Maintainence Module-15%
Completion of Label Printing Module- 15%
F | 6 | 4 | 66% | Completion of UAT- 10%
Production Go live - 10%
G | 5 | 3 | 60% | Production migration and Upgrade- 15%
Go Live- 30% -
H | 2 | 1 | 50% | 50% on UAT
I | 10 | 5 | 50% | Integrated Testing - 10%
Training - 10%
UAT - 10%
Production Preparedness & Surface Testing - 10%
Go Live - 10%

## Quality Analysis
Project Name | Start Date | End Date | Project Manager | Status | % Completion | SPI | Indication
A | 2022-10-15 | 2023-07-31 | SJ | In Progress | 60% | 0.6 | The project is behind schedule.
B | 2023-02-01 | 2023-07-31 | AK | In Progress | 50% | 0.5 | The project has performed half the work it was supposed to at this point.
C | 2023-02-20 | 2023-08-31 | RD | Delayed | 25% | 0.63 | The project is slightly behind schedule.
D | 2023-02-01 | 2023-08-31 | AK | In Progress | 60% | 0.6 | The project is behind schedule.
E | 2023-12-16 | 2023-07-31 | SJ | In Progress | 60% | 0.6 | The project is behind schedule.
F | 2023-02-20 | 2023-08-31 | AK | In Progress | 66% | 0.66 | The project is slightly behind schedule.
G | 2023-04-17 | 2023-10-17 | YA | Delayed | 60% | 0.8 | The project is slightly ahead of schedule.
H | 2023-04-10 | 2023-06-30 | AK | In Progress | 50% | 1 | The project is on schedule.
I | 2023-02-01 | 2023-07-31 | AK | In Progress | 50% | 0.5 | The project is significantly behind schedule.

## Bugs Status
Module | Bugs | State
SOH | 0 | Open | Highest number of Bugs :
Receiving | 4 | Open
Ship Confirm | 7 | Open | Module | Bugs
Cycle count | 4 | Open | User Mang | 13
PAR Count | 2 | Open | Inspection Adhoc | 13
User Mang | 13 | Open | Ship Confirm | 7
Inspection Details | 4 | Reopen
Inspection Adhoc | 13 | Open | Lowest Number of Bugs:
Scheduler | 4 | Open | Module | Bugs
Physical Count | 3 | Open | SOH | 0
Maintenance Material Return | 1 | Open
Discrete Material Return | 1 | Open
Discrete Operation Completion | 3 | Reopen | Bugs Status Distribution:
Operation Completion | 1 | Open
|  |  | Bugs State | Percentage
|  |  | Open | 88.33%
|  |  | Reopen | 11.67%
Calculations: |  |  | Average Bugs: |  | This indicates that, on average, each module has around 4 to 5 reported bugs. While some modules may have more bugs, and others may have fewer.
4.2857
1) Bugs State Distribution
Number of bugs:
60
Number of bugs (Open):
53
Number of bugs (ReOpen):
7
% of Open Bugs =
88.3333
% of Reopen Bugs=
11.6667
2) Average Bugs:
no. of bugs/ Total no. of modules